## Entering_Tasks
ID | Name | Task Type
0 | New Product Launch
2 | Phase 1 - Initiating | Summary Task
3 | Identify the launch team | Summary Task
4 | Determine sales objectives
5 | Define launch goals (launch timing and publicity objectives)
6 | Determine partners (if needed)
7 | Identify channel partners
8 | Identify online opportunities
9 | Obtain launch budget approval
10 | Initiation Complete | Milestone
11 | Phase 2 -Planning | Summary Task
12 | Kickoff product launch | Summary Task
13 | Marketing
14 | Define creative brief
15 | Prepare Messaging Framework | Summary Task
16 | Review current literature and plan new requirements
17 | Define press release requirements
18 | Define product specification literature
19 | Define sales presentations
20 | Messaging Framework COMPLETE | Milestone
21 | Phase 3 - Execution | Summary Task
22 | Marketing | Summary Task
23 | Evaluate market and refine messaging
24 | Design and order final packaging
25 | Create press releases
26 | Create sales presentations
27 | Create sales, field, and product support training
28 | Update product forecasts based on market feedback and analysis
29 | Update launch plan based on forecast
30 | Execution Preparation Complete | Milestone
31 | Phase 4 - Release To Manufacture
32 | Final Quality Review
33 | Conduct final quality review | Milestone
34 | Product Release Information COMPLETE | Milestone
35 | Needed materials are on order or in stock. | Milestone
36 | Literature COMPLETE | Milestone
37 | Training COMPLETE | Milestone
Launch Product